## WBS
WBS - OpenWork Tasks (Live Edit) | Tên công việc | Trạng thái | Ưu tiên | Người phụ trách | Bắt đầu | Deadline | Ngày HT | Effort (h) | % HT | Phụ thuộc | Tags | Ghi chú | Reference Files
1.0 | Dự án OpenWork fork tích hợp AionUi | 進行中 | 高 | Nhân | 2026-07-11 | 2026-09-30 |  | 613 | 0 |  |  | Phase 1-12
2.0 | Phase 1: File Preview ✅ DONE (90%) | 完了 | 高 | Nhân |  |  | 2026-07-11 | 120 | 90 |  | preview | Hầu hết đã có sẵn trong OpenWork | 📄 apps/app/src/react-app/domains/session/artifacts/preview.tsx (entry point)
2.1 | PreviewPanel + ArtifactPanel (multi-tab) | 完了 | 高 | Nhân |  |  | 2026-07-11 | 16 | 100 |  | preview,core | preview.tsx + artifact-panel.tsx | 📄 preview.tsx 📄 artifact-panel.tsx 📄 preview-with-file-tree.tsx
2.2 | SlidesPreview (PPT/PPTX) — OfficeCLI | 完了 | 高 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | preview,pptx | viewers/slides-viewer.tsx | 📄 apps/app/src/react-app/domains/session/artifacts/viewers/slides-viewer.tsx
2.3 | DocumentPreview (DOCX) — Mammoth | 完了 | 高 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | preview,docx | viewers/document-viewer.tsx | 📄 apps/app/src/react-app/domains/session/artifacts/viewers/document-viewer.tsx
2.4 | SpreadsheetPreview (XLSX) — SheetJS | 完了 | 中 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | preview,xlsx | viewers/spreadsheet-viewer.tsx | 📄 apps/app/src/react-app/domains/session/artifacts/viewers/spreadsheet-viewer.tsx
2.5 | DiffViewer (side-by-side) | 完了 | 中 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | preview,diff | viewers/diff-viewer.tsx | 📄 apps/app/src/react-app/domains/session/artifacts/viewers/diff-viewer.tsx
2.6 | CodePreview — Shiki syntax highlight | 完了 | 中 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | preview,code | Shiki 4.0, 80+ langs | 📄 apps/app/src/lib/shiki.ts
2.7 | PDF / Image / Video / Audio preview | 完了 | 中 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | preview,media | Native browser elements | 📄 preview.tsx (dòng ~200-250)
2.8 | Inline text editor (CodeMirror) | 完了 | 中 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | preview,editor | artifact-text-editor.tsx | 📄 apps/app/src/react-app/domains/session/artifacts/artifact-text-editor.tsx
2.9 | Inline spreadsheet editor (SheetJS) | 完了 | 中 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | preview,editor | artifact-spreadsheet-editor.tsx + .ts | 📄 artifact-spreadsheet-editor.tsx 📄 artifact-spreadsheet-model.ts
2.10 | File classification (80+ extensions) | 完了 | 中 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | preview,classify | open-target.ts | 📄 apps/app/src/react-app/domains/session/artifacts/open-target.ts
2.11 | Icon mapping (file type → lucide icon) | 完了 | 中 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | preview,icon | artifact-icon.tsx | 📄 apps/app/src/react-app/domains/session/artifacts/artifact-icon.tsx
2.12 | Preview limits (5MB) | 完了 | 低 | Nhân |  |  | 2026-07-11 | 4 | 100 |  | preview,limits | preview-limits.ts | 📄 apps/app/src/react-app/domains/session/artifacts/preview-limits.ts
2.13 | Multi-tab drag reorder | 未着手 | 低 | Nhân |  |  |  | 4 | 0 | 2.1 | ui,tabs | Kéo thả tab artifact panel | 🔗 aionui:packages/desktop/src/renderer/.../PreviewTabs.tsx
3.0 | Phase 2: Skills / Assistants ✅ DONE (85%) | 完了 | 高 | Nhân |  |  | 2026-07-11 | 160 | 85 |  | skill | 40 skills đã có sẵn | 📄 .opencode/skills/ (48 folders) 📄 settings/pages/skills-view.tsx 📄 apps/server/src/skill-hub.ts
3.1 | Skills management UI (Settings) | 完了 | 高 | Nhân |  |  | 2026-07-11 | 24 | 100 |  | skill,ui | skills-view.tsx (1329 loc) | 📄 apps/app/src/react-app/domains/settings/pages/skills-view.tsx
3.2 | Cloud skill sharing | 完了 | 中 | Nhân |  |  | 2026-07-11 | 16 | 100 |  | skill,cloud | Skill hub server-side | 📄 apps/server/src/skill-hub.ts
3.3 | Plugin system | 完了 | 中 | Nhân |  |  | 2026-07-11 | 16 | 100 |  | skill,plugin | plugins-view.tsx | 📄 apps/app/src/react-app/domains/settings/pages/plugins-view.tsx
3.4 | Claude plugin bundle import | 完了 | 中 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | skill,claude | claude-plugin-bundle.ts | 📄 apps/app/src/lib/claude-plugin-bundle.ts
3.5 | Extension registry | 完了 | 中 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | skill,extension | extension-config.ts | 📄 apps/app/src/lib/extension-config.ts
3.6 | Skill research-assistant | 未着手 | 高 | Nhân |  |  |  | 8 | 0 |  | skill,research | Workflow research + doc reading | 📄 .opencode/skills/ (pattern từ skill khác)
3.7 | Skill citation-extractor | 未着手 | 中 | Nhân |  |  |  | 8 | 0 |  | skill,citation | Trích dẫn nguồn tự động | 📄 .opencode/skills/ (pattern)
3.8 | Skill note-synthesizer | 未着手 | 中 | Nhân |  |  |  | 8 | 0 |  | skill,notes | Gộp nhiều note thành 1 | 📄 .opencode/skills/planning-with-files/ (pattern tham khảo)
4.0 | Phase 3: Scheduled Tasks ✅ IN PROGRESS (83%) | 進行中 | 高 | Nhân | 2026-07-11 |  | 2026-07-12 | 38 | 83 |  | cron | S1-S5 done, còn E2E test | 📄 apps/server/src/scheduled/repo.ts 📄 apps/server/src/scheduled/scheduler.ts 📄 apps/server/src/scheduled/runner.ts 📄 apps/server/src/routes/scheduled.ts 📄 apps/app/.../scheduled/scheduled-tasks-view.tsx
4.1 | DB migration: cron_jobs table | 完了 | 高 | Nhân |  |  | 2026-07-12 | 2 | 100 |  | cron,db | schema + repo với CREATE TABLE IF NOT EXISTS | 📄 apps/server/src/scheduled/repo.ts
4.2 | Cron runner service (croner) | 完了 | 高 | Nhân |  |  | 2026-07-12 | 8 | 100 | 4.1 | cron,runner | In-process cron scheduler + test | 📄 apps/server/src/scheduled/scheduler.ts
4.3 | CRUD API routes | 完了 | 高 | Nhân |  |  | 2026-07-12 | 4 | 100 | 4.1 | cron,api | GET/POST/PUT/DELETE /api/scheduled + /api/scheduled/:id/run | 📄 apps/server/src/routes/scheduled.ts
4.4 | Settings UI page | 完了 | 高 | Nhân |  |  | 2026-07-12 | 12 | 100 | 4.3 | cron,ui | List + toggle enable/disable (chưa có create/edit dialog) | 📄 apps/app/src/react-app/domains/settings/scheduled/scheduled-tasks-view.tsx 📄 apps/app/.../sidebar/quick-actions-group.tsx
4.5 | Execution engine + conversation relay | 完了 | 高 | Nhân |  |  | 2026-07-12 | 8 | 100 | 4.2 | cron,exec | Create session, gửi prompt, skip-overlap, timeout | 📄 apps/server/src/scheduled/runner.ts
4.6 | E2E test | 未着手 | 中 | Nhân |  |  |  | 4 | 0 | 4.1-4.5 | cron,test | Verify cron chạy đúng giờ
5.0 | Phase 4: Remote Access ⚠️ EARLY (15%) | 未着手 | 低 | Nhân |  |  |  | 44 | 15 |  | channel | Chỉ có Telegram | 📄 apps/app/src/react-app/domains/settings/pages/messaging-view.tsx 📄 apps/orchestrator/src/
5.1 | Telegram integration | 完了 | 中 | Nhân |  |  | 2026-07-11 | 16 | 100 |  | channel,telegram | messaging-view.tsx + Router | 📄 app:settings/pages/messaging-view.tsx 📄 orchestrator/src/
5.2 | WebUI server (Bun + QR) | 未着手 | 低 | Nhân |  |  |  | 16 | 0 |  | channel,webui | Mobile access QR code | 🔗 aionui:packages/web-host/src/index.ts 🔗 aionui:scripts/webui.ts
5.3 | WhatsApp channel | 未着手 | 低 | Nhân |  |  |  | 12 | 0 |  | channel,whatsapp | whatsapp-web.js | 🔗 aionui:examples/ext-feishu/channels/ext-feishu-channel.js (channel adapter pattern)
6.0 | Phase 5: File Tree ✅ DONE (85%) | 完了 | 中 | Nhân |  |  | 2026-07-11 | 120 | 85 |  | file-tree | Đã có sẵn | 📄 apps/app/src/react-app/domains/session/panel/file-explorer-panel.tsx 📄 apps/server/src/routes/files.ts
6.1 | FileExplorerPanel (virtual + lazy) | 完了 | 中 | Nhân |  |  | 2026-07-11 | 24 | 100 |  | file-tree,ui | file-explorer-panel.tsx (346 loc) | 📄 apps/app/src/react-app/domains/session/panel/file-explorer-panel.tsx
6.2 | Server file API (dir/stat/read/write/...) | 完了 | 中 | Nhân |  |  | 2026-07-11 | 24 | 100 |  | file-tree,api | routes/files.ts | 📄 apps/server/src/routes/files.ts
6.3 | File sessions + conflict detection | 完了 | 中 | Nhân |  |  | 2026-07-11 | 16 | 100 |  | file-tree,sessions | file-sessions.ts | 📄 apps/server/src/services/file-sessions.ts
6.4 | Audit trail (file operations log) | 完了 | 中 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | file-tree,audit | audit.ts | 📄 apps/server/src/services/audit.ts
6.5 | Side-by-side preview + file tree | 完了 | 中 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | file-tree,preview | preview-with-file-tree.tsx | 📄 apps/app/src/react-app/domains/session/artifacts/preview-with-file-tree.tsx
6.6 | Inbox/Outbox artifact transfer | 完了 | 中 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | file-tree,transfer | routes/files.ts inbox/outbox | 📄 apps/server/src/routes/files.ts (inbox/outbox sections)
6.7 | Context menu (rename/delete/move) | 未着手 | 低 | Nhân |  |  |  | 4 | 0 | 6.1 | file-tree,menu | Click chuột phải | 🔗 aionui:packages/desktop/src/renderer/.../WorkspaceContextMenu.tsx
6.8 | Batch operations UI | 未着手 | 低 | Nhân |  |  |  | 4 | 0 | 6.1 | file-tree,batch | Select nhiều file
7.0 | Phase 6: Version History ✅ DONE (100%) | 完了 | 高 | Nhân |  |  | 2026-07-12 | 26 | 100 |  | history | Hoàn thành — snapshot + API + UI + diff | 📄 apps/server/src/file-snapshots.ts 📄 apps/server/src/snapshot-middleware.ts 📄 apps/server/src/routes/history.ts 📄 apps/app/.../file-history-panel.tsx 📄 apps/app/.../viewers/diff-viewer.tsx
7.1 | Revision tracking (mtimeMs:size) | 完了 | 高 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | history,revision | file-sessions.ts | 📄 apps/server/src/services/file-sessions.ts
7.2 | DiffViewer component | 完了 | 高 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | history,diff | diff-viewer.tsx | 📄 apps/app/src/react-app/domains/session/artifacts/viewers/diff-viewer.tsx
7.3 | Audit trail | 完了 | 高 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | history,audit | audit.ts | 📄 apps/server/src/services/audit.ts
7.4 | DB migration: file_snapshots | 完了 | 高 | Nhân |  |  | 2026-07-12 | 2 | 100 |  | history,db | file-snapshots.ts với CREATE TABLE IF NOT EXISTS | 📄 apps/server/src/file-snapshots.ts
7.5 | Auto-snapshot on save middleware | 完了 | 高 | Nhân |  |  | 2026-07-12 | 4 | 100 | 7.4 | history,snapshot | snapshot-middleware.ts + test | 📄 apps/server/src/snapshot-middleware.ts
7.6 | History API route | 完了 | 高 | Nhân |  |  | 2026-07-12 | 4 | 100 | 7.4 | history,api | GET list/diff/content + POST restore | 📄 apps/server/src/routes/history.ts
7.7 | History UI dropdown | 完了 | 高 | Nhân |  |  | 2026-07-12 | 8 | 100 | 7.6 | history,ui | FileHistoryPanel popover — History + All Changes tabs | 📄 apps/app/src/react-app/domains/session/artifacts/file-history-panel.tsx 📄 apps/app/.../hooks/use-file-history.ts
7.8 | Diff compare 2 versions | 完了 | 中 | Nhân |  |  | 2026-07-12 | 4 | 100 | 7.2,7.6 | history,diff | Server unified-diff + API endpoint | 📄 apps/server/src/diff.ts 📄 apps/server/src/routes/history.ts (diff endpoint)
8.0 | Phase 7: Multi-tab Sessions 🔶 PARTIAL (40%) | 未着手 | 中 | Nhân |  |  |  | 12 | 40 |  | sessions | Có building blocks, cần tab strip | 📄 apps/app/src/react-app/domains/session/sidebar/app-sidebar.tsx 📄 panel-tab-store.ts 📄 side-panel.tsx
8.1 | Session sidebar + search/pin/groups | 完了 | 中 | Nhân |  |  | 2026-07-11 | 40 | 100 |  | sessions,sidebar | app-sidebar.tsx (1738 loc) | 📄 apps/app/src/react-app/domains/session/sidebar/app-sidebar.tsx
8.2 | Session groups (store + API) | 完了 | 中 | Nhân |  |  | 2026-07-11 | 24 | 100 |  | sessions,groups | session-management-store.ts + API | 📄 apps/app/src/lib/stores/session-management-store.ts 📄 apps/server/src/routes/sessions.ts
8.3 | Side-panel tabs (artifact + browser) | 完了 | 中 | Nhân |  |  | 2026-07-11 | 24 | 100 |  | sessions,panels | panel-tab-store.ts + side-panel.tsx | 📄 apps/app/src/lib/stores/panel-tab-store.ts 📄 apps/app/src/react-app/domains/session/panel/side-panel.tsx
8.4 | In-conversation tab strip | 未着手 | 中 | Nhân |  |  |  | 8 | 0 |  | sessions,tabs | Tab ngang chuyển conversation nhanh | 🔗 aionui:.../GroupedHistory/index.tsx 🔗 aionui:.../GroupedHistory/ConversationRow.tsx
8.5 | Drag-drop tab reorder | 未着手 | 低 | Nhân |  |  |  | 4 | 0 | 8.4 | sessions,drag | Dùng motion/react (đã có) | 📄 app-sidebar.tsx (motion/react Reorder — pattern có sẵn)
9.0 | Phase 8: Multi-Agent Team ❌ NONE | 保留 | 低 | Nhân |  |  |  | 60 | 0 |  | team | Không ưu tiên — phức tạp | 🔗 aionui:packages/desktop/src/renderer/pages/team/ (toàn bộ folder)
9.1 | DB: teams, team_members, mailbox | 保留 | 低 | Nhân |  |  |  | 4 | 0 |  | team,db | Schema | 🔗 aionui:packages/desktop/src/common/types/team/teamTypes.ts
9.2 | ACP SDK integration | 保留 | 低 | Nhân |  |  |  | 16 | 0 |  | team,acp | @agentclientprotocol/sdk | 🔗 aionui:.../platforms/acp/AcpChat.tsx
9.3 | Team UI page + chat view | 保留 | 低 | Nhân |  |  |  | 24 | 0 |  | team,ui | Member cards, slot view | 🔗 aionui:.../team/TeamPage.tsx 🔗 aionui:.../team/TeamChatView.tsx
9.4 | Leader delegation logic | 保留 | 低 | Nhân |  |  |  | 16 | 0 |  | team,logic | Analyze → delegate → summarize | 🔗 aionui:.../team/hooks/useTeamSession.ts
10.0 | Phase 9: MCP Management ✅ DONE (90%) | 完了 | 中 | Nhân |  |  | 2026-07-11 | 40 | 90 |  | mcp | Full UI + auth + marketplace | 📄 apps/app/src/react-app/domains/settings/pages/mcp-view.tsx 📄 apps/server/src/mcp.ts
10.1 | MCP Settings view (list + status) | 完了 | 中 | Nhân |  |  | 2026-07-11 | 16 | 100 |  | mcp,ui | mcp-view.tsx (1262 loc) | 📄 apps/app/src/react-app/domains/settings/pages/mcp-view.tsx
10.2 | Add MCP modal + auth flows | 完了 | 中 | Nhân |  |  | 2026-07-11 | 16 | 100 |  | mcp,auth | add-mcp-modal.tsx + mcp-auth-modal.tsx | 📄 add-mcp-modal.tsx 📄 mcp-auth-modal.tsx 📄 mcp-silent-reauth.ts
10.3 | Claude plugin import | 完了 | 中 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | mcp,claude | claude-plugin-import-modal.tsx | 📄 apps/app/src/react-app/domains/connections/modals/claude-plugin-import-modal.tsx
10.4 | Server MCP config + cloud plugins | 完了 | 中 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | mcp,server | mcp.ts + cloud-plugins.ts | 📄 apps/server/src/mcp.ts 📄 apps/app/src/lib/cloud-plugins.ts
11.0 | Phase 10: Custom CSS ❌ NONE | 未着手 | 中 | Nhân |  |  |  | 10 | 0 |  | theme | Easy win — 2 ngày | 🔗 aionui:.../AppearanceSettings/CssThemeSettings.tsx 🔗 aionui:.../AppearanceSettings/CssThemeModal.tsx
11.1 | CSS injector utility | 未着手 | 中 | Nhân |  |  |  | 2 | 0 |  | theme,injector | Inject/eject <style> | 🔗 aionui:.../AppearanceSettings/useCustomCSS.ts
11.2 | Settings UI (editor + live preview) | 未着手 | 中 | Nhân |  |  |  | 4 | 0 | 11.1 | theme,ui | Code editor + iframe preview | 🔗 aionui:.../CssThemeSettings.tsx 🔗 aionui:.../CssThemeModal.tsx
11.3 | Preset themes | 未着手 | 低 | Nhân |  |  |  | 2 | 0 |  | theme,presets | 1-2 theme mẫu | 🔗 aionui:.../AppearanceSettings/presets/default.css 🔗 aionui:.../AppearanceSettings/presets.ts
11.4 | Persist to localStorage | 未着手 | 中 | Nhân |  |  |  | 2 | 0 | 11.1 | theme,persist | Lưu CSS giữa sessions | 📄 apps/app/src/lib/stores/ (zustand persist pattern)
12.0 | Phase 11: Image Generation ⚠️ EARLY (25%) | 未着手 | 高 | Nhân |  |  |  | 14 | 25 |  | image-gen | Priority 2 — extension đã có | 📄 apps/app/src/react-app/domains/settings/openai-image-gen-config.tsx 📄 apps/app/src/lib/extensions/openai-image-extension.ts
12.1 | Extension config + settings UI | 完了 | 高 | Nhân |  |  | 2026-07-11 | 8 | 100 |  | image-gen,settings | openai-image-gen-config.tsx | 📄 apps/app/src/react-app/domains/settings/openai-image-gen-config.tsx
12.2 | Extension registration (image_generate) | 完了 | 高 | Nhân |  |  | 2026-07-11 | 4 | 100 |  | image-gen,ext | openai-image-extension.ts | 📄 apps/app/src/lib/extensions/openai-image-extension.ts
12.3 | Skill image-gen SKILL.md | 未着手 | 高 | Nhân |  |  |  | 4 | 0 |  | image-gen,skill | .opencode/skills/image-gen/ | 🔗 aionui:packages/desktop/src/common/chat/imageGenCore.ts 📄 .opencode/skills/ppt-creator/SKILL.md (pattern)
12.4 | In-chat image render | 未着手 | 中 | Nhân |  |  |  | 2 | 0 |  | image-gen,render | Hiển thị ảnh trong message | 📄 viewers/image-viewer.tsx (đã có)
12.5 | Built-in MCP server (optional) | 未着手 | 低 | Nhân |  |  |  | 8 | 0 |  | image-gen,mcp | MCP server như AionUi | 🔗 aionui:packages/desktop/src/process/resources/builtinMcp/imageGenServer.ts 🔗 aionui:.../imageGenerationMcpEnv.ts
13.0 | Phase 12: Right Panel UX (MiniMax-style) ✅ DONE (60%) | 完了 | 中 | Nhân | 2026-07-11 |  | 2026-07-12 | 18 | 60 |  | ui,panel | Hợp nhất 2 panel → 1 panel với 3 nút toggle | 📄 docs/ux-spec-side-panel-minimax-style.md 📄 panel/right-panel.tsx 📄 panel/file-explorer-panel.tsx 📄 panel/file-explorer-store.ts 📄 panel/panel-tab-store.ts
13.1 | UX Spec đầy đủ (13 bước) | 完了 | 中 | Nhân | 2026-07-11 |  | 2026-07-11 | 2 | 100 |  | ui,spec | docs/ux-spec-side-panel-minimax-style.md | 📄 docs/ux-spec-side-panel-minimax-style.md
13.2 | <RightPanel /> component (3-button toggle) | 完了 | 高 | Nhân | 2026-07-11 |  | 2026-07-11 | 4 | 100 | 13.1 | ui,react | Files / Preview / Browser + ⋯ + × | 📄 apps/app/src/react-app/domains/session/panel/right-panel.tsx
13.3 | Refactor <SessionPage /> mount 1 panel | 完了 | 高 | Nhân | 2026-07-11 |  | 2026-07-11 | 3 | 100 | 13.2 | ui,refactor | Bỏ switch FileExplorerPanel/SidePanel | 📄 apps/app/src/react-app/domains/session/chat/session-page.tsx
13.4 | Nút Reload artifact (RefreshCw) | 完了 | 中 | Nhân | 2026-07-11 |  | 2026-07-11 | 1 | 100 | 13.2 | ui,reload | Header button + invalidate query | 📄 apps/app/src/react-app/domains/session/artifacts/artifact-panel.tsx
13.5 | Auto-reload polling 3s | 完了 | 中 | Nhân | 2026-07-11 |  | 2026-07-11 | 2 | 100 | 13.4 | ui,polling | statWorkspaceFile + visibility check | 📄 apps/app/src/react-app/domains/session/artifacts/artifact-panel.tsx
13.6 | File tree search (diacritic + multi-word) | 完了 | 中 | Nhân | 2026-07-11 |  | 2026-07-11 | 2 | 100 | 13.2 | ui,search | Auto-expand kết quả | 📄 apps/app/src/react-app/domains/session/panel/file-explorer-panel.tsx
13.7 | 'Open in editor' context menu (7 editors) | 完了 | 低 | Nhân | 2026-07-11 |  | 2026-07-11 | 2 | 100 | 13.2 | ui,editor | VS Code/Cursor/Sublime/WebStorm/IDEA/nvim/vim | 📄 apps/app/src/app/lib/desktop.ts 📄 apps/desktop/electron/main.mjs
13.8 | File-explorer-store (persisted per workspace) | 完了 | 中 | Nhân | 2026-07-11 |  | 2026-07-12 | 1 | 100 | 13.2 | ui,store | Zustand + persist localStorage | 📄 apps/app/src/react-app/domains/session/panel/file-explorer-store.ts
13.9 | Persist artifact tabs (key v1→v2) | 完了 | 中 | Nhân | 2026-07-11 |  | 2026-07-12 | 1 | 100 | 13.8 | ui,persist | Restore tabs khi mở lại session | 📄 apps/app/src/react-app/domains/session/panel/panel-tab-store.ts
13.10 | Auto-expand ancestor khi mở file | 完了 | 中 | Nhân | 2026-07-12 |  | 2026-07-12 | 1 | 100 | 13.8 | ui,reveal | expandAncestors(workspaceId, filePath) | 📄 apps/app/src/react-app/domains/session/panel/file-explorer-store.ts
13.11 | Sync tree selection với active tab | 完了 | 中 | Nhân | 2026-07-12 |  | 2026-07-12 | 1 | 100 | 13.10 | ui,sync | Watch activeTabId → highlight + expand | 📄 apps/app/src/react-app/domains/session/panel/file-explorer-panel.tsx
13.12 | Bugfix: infinite render loop | 完了 | 高 | Nhân | 2026-07-12 |  | 2026-07-12 | 0.5 | 100 | 13.8 | bugfix | Hook return array thay vì Set mới | 📄 apps/app/src/react-app/domains/session/panel/file-explorer-store.ts
13.13 | Bugfix: tree descendants bị wipe | 完了 | 高 | Nhân | 2026-07-12 |  | 2026-07-12 | 0.5 | 100 | 13.6 | bugfix | Bỏ effect rebuild tree | 📄 apps/app/src/react-app/domains/session/panel/file-explorer-panel.tsx
13.14 | Bugfix: empty state cho returning workspace | 完了 | 高 | Nhân | 2026-07-12 |  | 2026-07-12 | 0.5 | 100 | 13.8 | bugfix | Luôn setTree khi data load | 📄 apps/app/src/react-app/domains/session/panel/file-explorer-panel.tsx
13.15 | Keyboard shortcuts (Cmd+Shift+F/P/B) | 未着手 | 中 | Nhân |  |  |  | 1 | 0 | 13.2 | ui,keyboard | Mở nhanh 3 mode + Esc/Cmd+. đóng | 📄 apps/app/src/react-app/shell/use-shell-shortcuts.ts
13.16 | Empty states polish (3 mode) | 未着手 | 低 | Nhân |  |  |  | 0.5 | 0 | 13.2 | ui,empty | Empty state rõ ràng cho files/preview/browser
13.17 | Optimize polling (1 interval per session) | 未着手 | 低 | Nhân |  |  |  | 1.5 | 0 | 13.5 | ui,perf | Gộp polling thay vì mỗi ArtifactPanel 1 interval
13.18 | Drag file từ tree vào chat | 未着手 | 中 | Nhân |  |  |  | 2.5 | 0 | 13.2 | ui,drag | @file/path mention khi kéo thả
99.0 | TỔNG HỢP | [6 empty] | 588 | 0

## Legend
CHÚ THÍCH WBS
TRẠNG THÁI (Trạng thái)
完了 | Hoàn thành
進行中 | Đang làm
未着手 | Chưa bắt đầu
保留 | Tạm hoãn
ƯU TIÊN (Ưu tiên)
高 | Cao
中 | Trung bình
低 | Thấp
WBS NUMBERING
1 | Phase / Module
1.1 | Task trong phase
1.1.1 | Sub-task (nếu có)
CÁCH DÙNG
1. Mở file bằng Excel hoặc LibreOffice
2. Click header để sort / filter
3. Màu tự động theo trạng thái và ưu tiên
4. Sửa trực tiếp, hoặc dùng OfficeCLI:
officecli set wbs-tasks-vi.xlsx /WBS/A2 --prop value=完了
BẢO TRÌ
Để thêm task mới, copy 1 dòng rồi sửa WBS number
Mỗi phase nên có ít nhất 1 task mới khi mở rộng

## Tổng quan
TỔNG QUAN DỰ ÁN
Dự án: | OpenWork fork tích hợp AionUi
Mục tiêu: | File preview + Skills cho research workflow
Bắt đầu: | 2026-07-11
Deadline: | 2026-09-30
Owner: | Nhân
PHASE | TRẠNG THÁI | TASK | EFFORT (h)
1. Phân tích & quyết định | 完了 | 4/4 | 68
2. Phase 1: File Preview | 進行中 | 1/7 | 120
3. Phase 2: Skills research | 未着手 | 0/6 | 160
4. Phase 3: File tree + version | 未着手 | 0/5 | 120
5. Phase 4: Polish + test | 未着手 | 0/3 | 120
6. Backlog | 保留 | 0/6 | 0
TỔNG |  | 5/31 | 588
GHI CHÚ
• Sheet WBS chứa chi tiết tất cả task
• Sheet Legend giải thích ký hiệu
• Sheet Backlog cho phase 6 (làm sau)
• Cột C tự đổi màu theo trạng thái
• Cột D tự đổi màu theo ưu tiên
• Cột I (Effort) có data bar xanh
• Cột J (% HT) có data bar xanh lá

## Backlog
BACKLOG — Phase 6 (Làm sau)
Các tính năng nâng cao, ưu tiên thấp hơn core
TÍNH NĂNG | ƯU TIÊN | GHI CHÚ
Scheduled tasks (cron 24/7) | 低 | Đã có plan trong port guide, port từ AionUi
Remote access (Telegram/Lark) | 低 | Phức tạp, ít cần cho use case research
Multi-agent Team Mode (ACP) | 中 | Cần khi scale lên nhiều workflow song song
MCP unified management | 中 | Config 1 lần cho mọi agent
Custom CSS theming | 低 | Nice-to-have, không ảnh hưởng chức năng
Image generation | 低 | Thêm sau khi core stable
PPT Morph transition | 低 | Nếu cần tạo slide đẹp, dùng OfficeCLI tạo rồi Office thêm animation
3D Game assistant | 低 | Không liên quan tới use case research
Story Roleplay | 低 | Fun-to-have, không phải core
Khi nào review backlog?
• Khi Phase 1-4 xong (dự kiến 2026-10)
• Khi cần automation chạy 24/7 (cron)
• Khi muốn điều khiển từ xa (Telegram)
• Khi muốn scale multi-agent

## Tong quan
TỔNG QUAN DỰ ÁN
Dự án: | OpenWork fork tích hợp AionUi
Mục tiêu: | File preview + Skills + Version History + Cron
Bắt đầu: | 2026-07-11
Deadline: | 2026-09-30
Owner: | Nhân
PHASE | TRẠNG THÁI | DONE/TOTAL | EFFORT (h)
1. File Preview | ✅ DONE (90%) | 12/13 | 120
2. Skills / Assistants | ✅ DONE (85%) | 5/9 | 160
3. Scheduled Tasks | ✅ IN PROGRESS (83%) | 5/6 | 38
4. Remote Access | ⚠️ EARLY (15%) | 1/3 | 44
5. File Tree | ✅ DONE (85%) | 6/8 | 120
6. Version History | ✅ DONE (100%) | 8/8 | 26
7. Multi-tab Sessions | 🔶 PARTIAL (40%) | 3/5 | 12
8. Multi-Agent Team | ❌ NONE (0%) | 0/5 | 60
9. MCP Management | ✅ DONE (90%) | 4/4 | 40
10. Custom CSS | ❌ NONE (0%) | 0/4 | 10
11. Image Generation | ⚠️ EARLY (25%) | 2/5 | 14
12. Right Panel UX (MiniMax-style) | ✅ DONE (60%) | 14/18 | 18
TỔNG |  | 66/99 | 613
Ghi chú: | Cột Reference Files chứa đường dẫn file cần đọc
📄 = file trong OpenWork | 🔗 = file trong AionUi cần port